## Fall
GANTT CHART
PROJECT TITLE | Application of Machine Learning in Heart Attack Risk Analysis
PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Results Evaluation and Analysis | Jialuo Li | 2025-11-08 | 2025-11-16 | 8 | bar: 2025-11-10 M to 2025-11-17 U; 2025-12-01 M to 2025-12-01 U
Evaluation
Model Comparison | Jiahui Zhang | 2025-11-18 | 2025-11-27 | 9 | bar: 2025-11-17 M to 2025-11-24 R; 2025-12-01 M to 2025-12-01 U
Presentation | Qinxuan Li | 2025-11-20 | 2025-11-30 | 10 | bar: 2025-11-17 M to 2025-12-01 U
Recording | Jiannan Huang | 2025-11-25 | 2025-12-02 | 7 | bar: 2025-11-17 M to 2025-11-17 U; 2025-11-24 T to 2025-12-01 U
Final Report | Binfei Li | 2025-11-27 | 2025-12-02 | 5 | bar: 2025-11-17 M to 2025-11-17 U; 2025-11-24 R to 2025-12-01 U